## Tasks
Chevron Lekki Critical Power Equipment (RMU) Monitoring Project Timelines
No. | Start | End | Task
1 | 2025-09-03 | 2025-09-03 | Project Kickoff Meeting
2 | 2025-09-03 | 2025-09-12 | Detailed Site Survey
3 |  |  | Inspection & Evaluation of Existing Control & Telemetry Infrastructure
4 |  |  | Inspection for Overall Architecture & Integration Plan
5 |  |  | Survey for Communication/Data (FOC etc. routes) Paths
6 |  |  | Survey for Equipment & Panel Support
7 |  |  | Technical Engagement Session with CNL to Review Engineering Concept
| 2025-09-15 | 2025-10-14 | Engineering
8 |  |  | Detailed Integration Planning
9 |  |  | Development of Final Overall Architecture
10 |  |  | Hardware Location Plot & Cable Route Mapping
11 |  |  | Development of Final Harware MTO
12 |  |  | Updating of Control Philosophy to Capture The Smart RMUs
13 |  |  | Verification of Existing Software (PLC Logic Program & HMI Design) Backups
14 |  |  | Verification of Migration Compatibility from Current HMI Version to Latest Version
15 |  |  | Updating of PLC Logic
16 |  |  | Updating of HMI Graphics
17 |  |  | Development of Final List of Required Software
18 |  |  | Provide Final List of DED Deliverables for CNL Approval
19 |  |  | Development of DED Documentation & Seek AFC
20 |  |  | Pre-decommissioning Program Backup & Logic Upgrading
21 | 2025-09-29 | 2025-10-20 | Procurement Part A (FOC, Media Converters & Control Hardwares)
22 | 2025-10-09 | 2025-10-20 | Procurement Part B (Software Licenses)
| 2025-10-27 | 2025-11-24 | Site Installation
23 |  |  | Mobilization of Personnels & Basic Tools
24 |  |  | Installation of Equipment & Panel Support
25 |  |  | Installation of Patch Panels & Media Converter Panels
26 |  |  | Installation of New MODBUS Card in PLC Panel (If necessary)
27 |  |  | Run Cables from Media Converter to PLC MODBUS Card
28 |  |  | Crimping, Termination & Testing of FOC Link
29 |  |  | Ternimation of TCP or Serial Cable at MODBUS Card
| 2025-11-24 | 2025-12-05 | Integration
30 |  |  | Simulate and Upload Updated PLC Program
31 |  |  | Simulate and Upload Updated HMI Graphics
32 |  |  | Verify PLC Program & HMI Graphics after Installation on Client Machine
33 | 2025-12-05 | 2025-12-10 | iSAT & Commissioning
34 | 2025-11-24 | 2025-12-14 | MOC/As-Built Documentation
35 | 2025-12-15 | 2025-12-15 | Handing Over & Demobilization